ASINA DISABILITY SERVICES

STRATEGIC AND OPERATIONAL PLAN 2026-2028

Policy and Procedure

| Document ID |  |
| --- | --- |
| Version | 1.0 |
| Effective Date | March 2026 |
| Review Date | March 2027 |
| Approved By | Director |
| Classification | Internal |

CONFIDENTIAL

This document is the property of Asina Disability Services. Unauthorised reproduction or distribution is prohibited.

# Table of Contents

# 1. Executive Summary

This Strategic and Operational Plan sets out the vision, mission, values, and strategic priorities for Asina Disability Services for the period 2026-2028. It provides a framework for decision-making, resource allocation, and performance measurement as the organisation establishes itself as a registered NDIS provider in New South Wales.

# 2. About Asina Disability Services

Asina Disability Services is a new NDIS provider committed to delivering high-quality, person-centred disability support services. The organisation is working towards NDIS registration and will provide services including Supported Independent Living (SIL), community access, assistance with daily living, transport, meal preparation, drop-in support, and capacity building.

## 2.1 Vision

To be a trusted provider of disability services that empowers participants to live their best lives with dignity, choice, and independence.

## 2.2 Mission

To deliver safe, responsive, and person-centred disability support services that meet the needs and goals of each participant, while maintaining the highest standards of quality and compliance.

## 2.3 Values

- Person-Centred: We place participants at the centre of everything we do

- Respect: We uphold the dignity, rights, and choices of every person

- Safety: We prioritise the safety and wellbeing of participants and staff

- Integrity: We act ethically, transparently, and accountably

- Excellence: We strive for continuous improvement in all aspects of service delivery

- Inclusion: We embrace diversity and promote equal access for all

# 3. Strategic Priorities 2026-2028

## 3.1 Priority 1: Achieve and Maintain NDIS Registration

Objective: Successfully register as an NDIS provider before July 2026

- Complete all required policies and procedures (Target: April 2026)

- Implement quality management system (Target: April 2026)

- Submit registration application to NDIS Commission (Target: May 2026)

- Complete certification audit (Target: June 2026)

- Maintain ongoing compliance with NDIS Practice Standards

Key Performance Indicators:

- Registration achieved by July 2026

- Zero critical non-conformities at audit

- 100% of policies reviewed within scheduled timeframes

## 3.2 Priority 2: Build Workforce Capability

Objective: Recruit, train, and retain a skilled and compliant workforce

- Recruit initial support workers (Target: March-April 2026)

- Implement comprehensive induction program

- Ensure 100% NDIS Worker Screening compliance

- Establish supervision and performance management framework

- Develop ongoing training calendar aligned to Practice Standards

Key Performance Indicators:

- All staff complete induction within first week

- 100% worker screening clearance maintained

- Minimum 80% staff satisfaction rate

- Staff turnover below 20% annually

## 3.3 Priority 3: Deliver High-Quality Services

Objective: Establish and grow service delivery with a focus on participant outcomes

- Commence service delivery following registration

- Implement individual support planning processes

- Establish participant feedback mechanisms

- Achieve positive participant outcomes and satisfaction

- Grow participant base through quality reputation

Key Performance Indicators:

- Minimum 90% participant satisfaction rate

- All participants have current individual support plans

- Participant goals reviewed quarterly

- Complaints resolved within target timeframes

## 3.4 Priority 4: Financial Sustainability

Objective: Establish sound financial management and achieve sustainability

- Develop and implement financial management systems

- Ensure NDIS pricing compliance and accurate invoicing

- Monitor cash flow and budget performance monthly

- Achieve financial break-even within 12 months of service commencement

Key Performance Indicators:

- Monthly financial reporting established

- NDIS claims accuracy above 98%

- Operating within approved budget

## 3.5 Priority 5: Continuous Improvement

Objective: Embed a culture of quality improvement across the organisation

- Implement Quality Improvement Register and processes

- Conduct regular internal audits against Practice Standards

- Analyse incidents, complaints, and feedback for trends

- Action improvements and track outcomes

Key Performance Indicators:

- Minimum 4 quality improvement actions per year

- Internal audits completed per schedule

- All improvement actions tracked to completion

# 4. Operational Plan 2026-2027

| Quarter | Key Actions | Responsible | Status |
| --- | --- | --- | --- |
| Q1 2026 (Jan-Mar) | Complete policies and procedures Set up quality management system Recruit initial support workers Begin worker screening processes | Director | In Progress |
| Q2 2026 (Apr-Jun) | Submit NDIS registration application Complete staff induction and training Prepare for certification audit Establish financial systems | Director | Planned |
| Q3 2026 (Jul-Sep) | Achieve NDIS registration Commence registered service delivery Onboard initial participants First internal audit cycle | Director / Ops Manager | Planned |
| Q4 2026 (Oct-Dec) | Review and improve processes Expand workforce as needed Participant satisfaction surveys Financial review and forecasting | Director / Ops Manager | Planned |
| Q1 2027 (Jan-Mar) | Annual policy review cycle Strategic plan review Workforce development review Quality improvement reporting | Director / Ops Manager | Planned |
| Q2 2027 (Apr-Jun) | Mid-cycle audit preparation Service expansion planning Staff training program refresh Participant outcome reviews | Director / Ops Manager | Planned |

# 5. Risk Management

Key strategic risks and mitigations are managed through the Risk Management Policy (POL-GOV-002) and the Risk Register. Priority strategic risks include:

- Failure to achieve registration: Mitigated by thorough preparation and gap analysis

- Difficulty recruiting quality staff: Mitigated by competitive conditions and positive culture

- Financial sustainability: Mitigated by careful budgeting and staged growth

- Compliance failure: Mitigated by robust quality management system

# 6. Monitoring and Review

This plan will be monitored and reviewed through:

- Quarterly review of KPIs and operational actions by the Director

- Annual strategic plan review and refresh

- Continuous quality improvement processes

- Feedback from participants, staff, and stakeholders

The next full review of this Strategic and Operational Plan is scheduled for March 2027.